## Sprint 01
Movie Threater
Sprint | PIC | Module | Module detail | Start Date | End Date | Status
1 | Mai Phong | FE: Create Base Project |  | 19/12/2024 | 2024-12-28
|  | FE: Authenication | - Develop login, registration pages
- Implement form validation and handle error messages from the backend.
|  | BE: Authenication | - Create entities, repositories, services, controllers, SecurityFilterandConfiguration for Authenication.
- Validate form input data
|  | FE: User management | - Develop user profile pages for USER
- Develop a user listing page with paging and filter (sort, search,…) for ADMIN
|  | BE: User management | - Create entities, repositories, services, controllers for User Management
- Implement authentication and authorization using JWT.
|  | FE: Employee management | - Develop pages for create/update employee
- Implement form validation and handle error messages from the backend.
|  | BE: Employee management | - Create entities, repositories, services, controllers for Employee Management
- Validate form input data
| Nguyễn Hiển | BASE: Details Design database | - Read the requirements for all modules across the 3 sprints. - Carefully review the requirements for the modules in Sprint 1. - Identify the necessary entities. - Design the ERD (Crowfoot/Peter Chen notation). | 19/12/2024 | 2024-12-28
BASE: Create Q&A
|  | FE: Movie management | - Develop pages/forms for create/update employee
- Create a movie listing page with paging and filters (by genre, release date, …)
|  | BE: Movie management | - Create entities, repositories, services, controllers for Movie Management
- Validate form input data
|  | FE: Create pages | Create Home page
Create About page
Create Contact page
| Nguyễn Quang | BE: Create Base Project |  | 19/12/2024 | 2024-12-28
|  | BASE: Create module management file | - Read the requirements for all modules across the 3 sprints. - Assigning tasks to team members
|  | FE: Cinema management | - Develop pages/forms for create/update employee
- Create a cinema listing page with paging and filters (by genre, release date, …)
|  | BE: Cinema management | - Create entities, repositories, services, controllers for Cinema Management
- Validate form input data
|  | FE: Promotion management | - Develop pages/forms for create/update employee
- Create a promotion listing page with paging and filters (by genre, release date, …)
|  | BE: Promotion management | - Create entities, repositories, services, controllers for Promotion Management
- Validate form input data
Tổng kết Sprint 1: Implement Authentication (login, register), movie, employee, cinema manager (BE + FE)
Sprint 2: Promotion management, Ticket booking, selling(User-admin-employee), booked ticket management of user (User), booked ticket management(Admin), cinemaroom management
2 | Mai Phong | Booked ticket management of user(user) |  | 2024-12-29 | 2024-01-08
Ticket booking(user)
| Nguyễn Hiển | Ticket selling(employee, admin)
Booked ticket management(admin)
| Nguyễn Quang | Cinema room management
Promotion management
Sprint 3: Email service, FE decoration, Add functional (banner, list of newest movie, list of best seller movie, list of highest rating movie, review movie, payment, AI,...)
3 | Mai Phong |  |  | 2024-01-09 | 2024-01-19
Nguyễn Hiển
Nguyễn Quang